## Dashboard
CERPA WORKBOOK — DASHBOARD
30 |  | 25 |  | 20 | 15 |  | 10
Total Claims |  | Total Events |  | Total Reviews | Total Patches |  | Applied
DRIFT METRICS |  |  |  |  | PATCH STATUS
Drift Detected (Y) | 11 |  | Events w/ Deviation | 17 | Applied | 4
No Drift (N) | 9 |  | Events w/o Deviation | 8 | Approved | 7
Drift Rate | 55% |  |  |  | Pending | 4
SEVERITY DISTRIBUTION |  |  | CLAIM STATUS
Critical | 3 |  | Open | 18
High | 4 |  | Under Review | 4
Medium | 6 |  | Patched | 4
Low | 7 |  | Closed | 4
HOW TO USE THIS WORKBOOK
1. CLAIMS tab: Register every decision, requirement, or assertion as a new row with a unique ClaimID.
2. EVENTS tab: Log what actually happened. Link each Event to its ClaimID. Flag deviations.
3. REVIEWS tab: Compare Claims vs Events. Detect drift. Assign severity. Link to both ClaimID and EventID.
4. PATCHES tab: Document corrections. Link to the ReviewID that triggered it and the ClaimID being corrected.
5. APPLY tab: Record when corrections go live. Link to PatchID and ClaimID. Attach evidence.
6. AUDIT: Filter any tab by ClaimID to see the full lifecycle. Export filtered tabs to PDF for evidence package.
7. DASHBOARD: This tab auto-calculates metrics from the five CERPA tabs. Refresh by pressing Ctrl+Shift+F9.

## Claims
ClaimID | Date | Owner | Description | Source | Status | LinkedEventIDs
CLM-001 | 2025-10-11 | MAJ Torres (COR) | Contractor shall deliver monthly status report by 5th business day | SOW Para 3.1 | Open | EVT-001
CLM-002 | 2025-10-01 | CPT Chen (ACOR) | All software deliverables shall pass security scan before acceptance | SOW Para 3.2 | Closed | EVT-002
CLM-003 | 2025-10-05 | Mr. Davis (KO) | Contractor shall maintain 98% system uptime during core hours | SOW Para 4.1 | Open | EVT-003
CLM-004 | 2025-10-04 | Ms. Patel (PM) | Weekly staffing report due every Monday by 1200 | SOW Para 5.3 | Open | EVT-004
CLM-005 | 2025-10-12 | SSG Miller (QA) | All personnel shall hold current security clearance at TS/SCI level | CDRL A001 | Open | EVT-005
CLM-006 | 2025-10-11 | MAJ Torres (COR) | Help desk response time shall not exceed 15 minutes during business hours | CDRL A003 | Closed | EVT-006
CLM-007 | 2025-10-15 | CPT Chen (ACOR) | Quarterly program review briefing delivered by 10th of quarter | CDRL A005 | Patched | EVT-007
CLM-008 | 2025-10-02 | Mr. Davis (KO) | All code commits shall include unit test coverage above 80% | PWS 3.2.1 | Patched | EVT-008
CLM-009 | 2025-10-07 | Ms. Patel (PM) | Contractor shall provide 24/7 on-call support for critical systems | PWS 4.1.3 | Open | EVT-009
CLM-010 | 2025-10-01 | SSG Miller (QA) | Data backup completed nightly with verification log provided weekly | QASP Para 2 | Open | EVT-010
CLM-011 | 2025-10-04 | MAJ Torres (COR) | Network monitoring dashboard updated in real-time with 5-min refresh | QASP Para 4 | Open | EVT-011
CLM-012 | 2025-10-09 | CPT Chen (ACOR) | Incident response initiated within 30 minutes of detection | TO Mod 001 | Patched | EVT-012
CLM-013 | 2025-10-01 | Mr. Davis (KO) | All documentation delivered in accordance with DI-MGMT-81466 | TO Mod 003 | Patched | EVT-013
CLM-014 | 2025-10-04 | Ms. Patel (PM) | Training materials updated within 30 days of system change | Policy Memo 24-01 | Closed | EVT-014
CLM-015 | 2025-10-11 | SSG Miller (QA) | Transition plan delivered 90 days before period of performance end | COR Direction 25-001 | Closed | EVT-015
CLM-016 | 2025-10-09 | MAJ Torres (COR) | Contractor shall comply with NIST 800-171 requirements | SOW Para 3.1 | Under Review | EVT-016
CLM-017 | 2025-10-04 | CPT Chen (ACOR) | Configuration management plan maintained and current | SOW Para 3.2 | Under Review | EVT-017
CLM-018 | 2025-10-10 | Mr. Davis (KO) | System patches applied within 72 hours of release for critical CVEs | SOW Para 4.1 | Open | EVT-018
CLM-019 | 2025-10-13 | Ms. Patel (PM) | All travel requires prior written COR approval | SOW Para 5.3 | Open | EVT-019
CLM-020 | 2025-10-13 | SSG Miller (QA) | Monthly financial report with cost/burn-rate analysis by 10th | CDRL A001 | Open | EVT-020
CLM-021 | 2025-10-12 | MAJ Torres (COR) | Risk register maintained and reviewed at each program review | CDRL A003 | Under Review | EVT-021
CLM-022 | 2025-10-06 | CPT Chen (ACOR) | Contractor key personnel changes require 30-day advance notice | CDRL A005 | Open | EVT-022
CLM-023 | 2025-10-03 | Mr. Davis (KO) | All government-furnished equipment tracked in property log | PWS 3.2.1 | Open | EVT-023
CLM-024 | 2025-10-13 | Ms. Patel (PM) | Test plan delivered and approved before system testing begins | PWS 4.1.3 | Open | EVT-024
CLM-025 | 2025-10-02 | SSG Miller (QA) | Final delivery acceptance within 10 business days of submission | QASP Para 2 | Open | EVT-025
CLM-026 | 2025-10-07 | MAJ Torres (COR) | Contractor shall maintain ISO 27001 certification throughout PoP | QASP Para 4 | Open
CLM-027 | 2025-10-06 | CPT Chen (ACOR) | Sub-contractor performance monitored and reported quarterly | TO Mod 001 | Open
CLM-028 | 2025-10-10 | Mr. Davis (KO) | Earned Value Management reports delivered monthly per CDRL | TO Mod 003 | Open
CLM-029 | 2025-10-13 | Ms. Patel (PM) | Access control logs reviewed weekly by contractor security officer | Policy Memo 24-01 | Open
CLM-030 | 2025-10-12 | SSG Miller (QA) | Lessons learned report delivered within 30 days of milestone completion | COR Direction 25-001 | Under Review

## Events
EventID | Date | ClaimID | Observer | What Happened | Evidence | Deviation
EVT-001 | 2025-12-23 | CLM-001 | MAJ Torres (COR) | March status report delivered on 12th business day — 7 days late | \\fileserver\TO-Evidence\EVT-001.pdf | N
EVT-002 | 2025-10-26 | CLM-002 | SSG Miller (QA) | Security scan completed; 3 critical findings identified | \\fileserver\TO-Evidence\EVT-002.pdf | Y
EVT-003 | 2025-12-01 | CLM-003 | SSG Miller (QA) | System uptime measured at 94.2% for February — below 98% threshold | \\fileserver\TO-Evidence\EVT-003.pdf | Y
EVT-004 | 2025-10-24 | CLM-004 | MAJ Torres (COR) | Staffing report received Monday at 1430 — 2.5 hours late | \\fileserver\TO-Evidence\EVT-004.pdf | Y
EVT-005 | 2025-11-22 | CLM-005 | MAJ Torres (COR) | Personnel audit: 2 of 14 staff have expired interim clearances | \\fileserver\TO-Evidence\EVT-005.pdf | Y
EVT-006 | 2025-10-28 | CLM-006 | Ms. Patel (PM) | Help desk average response: 22 minutes — exceeds 15-min SLA | \\fileserver\TO-Evidence\EVT-006.pdf | Y
EVT-007 | 2025-12-13 | CLM-007 | Mr. Davis (KO) | Q1 program review delivered on time; content reviewed by COR | \\fileserver\TO-Evidence\EVT-007.pdf | Y
EVT-008 | 2025-12-02 | CLM-008 | Mr. Davis (KO) | Code coverage measured at 71% on Sprint 14 deliverable | \\fileserver\TO-Evidence\EVT-008.pdf | Y
EVT-009 | 2025-11-19 | CLM-009 | MAJ Torres (COR) | On-call technician unreachable for 45 minutes during Severity 1 event | \\fileserver\TO-Evidence\EVT-009.pdf | N
EVT-010 | 2025-11-06 | CLM-010 | SSG Miller (QA) | Backup verification log shows 3 failed backups in week of 3/15 | \\fileserver\TO-Evidence\EVT-010.pdf | Y
EVT-011 | 2025-11-05 | CLM-011 | Ms. Patel (PM) | Dashboard showed 15-minute data gap during maintenance window | \\fileserver\TO-Evidence\EVT-011.pdf | N
EVT-012 | 2025-11-19 | CLM-012 | SSG Miller (QA) | Incident response time: 47 minutes for P1 network outage on 3/22 | \\fileserver\TO-Evidence\EVT-012.pdf | Y
EVT-013 | 2025-11-26 | CLM-013 | MAJ Torres (COR) | Documentation format does not conform to DI-MGMT-81466 template | \\fileserver\TO-Evidence\EVT-013.pdf | Y
EVT-014 | 2025-10-20 | CLM-014 | Mr. Davis (KO) | Training materials reference deprecated system version (v2.1 vs v3.0) | \\fileserver\TO-Evidence\EVT-014.pdf | N
EVT-015 | 2025-11-19 | CLM-015 | MAJ Torres (COR) | Transition plan submitted on day 85 — 5 days late per SOW | \\fileserver\TO-Evidence\EVT-015.pdf | Y
EVT-016 | 2025-12-27 | CLM-016 | Mr. Davis (KO) | NIST 800-171 self-assessment score: 87/110 — 3 POAMs open | \\fileserver\TO-Evidence\EVT-016.pdf | Y
EVT-017 | 2025-12-18 | CLM-017 | Ms. Patel (PM) | CM plan last updated 6 months ago — does not reflect current architecture | \\fileserver\TO-Evidence\EVT-017.pdf | N
EVT-018 | 2025-11-03 | CLM-018 | Mr. Davis (KO) | Critical CVE patches applied in 96 hours — 24 hours over threshold | \\fileserver\TO-Evidence\EVT-018.pdf | Y
EVT-019 | 2025-11-16 | CLM-019 | SSG Miller (QA) | Contractor travel conducted without prior COR written approval | \\fileserver\TO-Evidence\EVT-019.pdf | N
EVT-020 | 2025-11-18 | CLM-020 | SSG Miller (QA) | Financial report delivered on 15th — 5 days late; burn rate missing | \\fileserver\TO-Evidence\EVT-020.pdf | N
EVT-021 | 2025-12-29 | CLM-021 | Ms. Patel (PM) | March status report delivered on 12th business day — 7 days late | \\fileserver\TO-Evidence\EVT-021.pdf | Y
EVT-022 | 2025-11-13 | CLM-022 | CPT Chen (ACOR) | Security scan completed; 3 critical findings identified | \\fileserver\TO-Evidence\EVT-022.pdf | N
EVT-023 | 2025-12-18 | CLM-023 | MAJ Torres (COR) | System uptime measured at 94.2% for February — below 98% threshold | \\fileserver\TO-Evidence\EVT-023.pdf | Y
EVT-024 | 2025-10-30 | CLM-024 | CPT Chen (ACOR) | Staffing report received Monday at 1430 — 2.5 hours late | \\fileserver\TO-Evidence\EVT-024.pdf | Y
EVT-025 | 2025-12-09 | CLM-025 | SSG Miller (QA) | Personnel audit: 2 of 14 staff have expired interim clearances | \\fileserver\TO-Evidence\EVT-025.pdf | Y

## Reviews
ReviewID | Date | ClaimID | EventID | Finding | Drift Detected | Severity | Reviewer
REV-001 | 2025-12-19 | CLM-001 | EVT-001 | Drift confirmed: 3 of last 4 reports late. Pattern, not one-time. | N | Critical | Mr. Jackson (QA)
REV-002 | 2026-01-06 | CLM-002 | EVT-002 | Security findings are valid Critical. Deliverable cannot be accepted. | Y | Low | MAJ Torres (COR)
REV-003 | 2026-01-26 | CLM-003 | EVT-003 | Uptime below threshold 2 consecutive months. Systemic issue. | Y | High | Ms. Kim (Audit)
REV-004 | 2026-01-21 | CLM-004 | EVT-004 | Minor deviation. Verbal counseling sufficient. Monitor next 4 weeks. | Y | Low | CPT Chen (ACOR)
REV-005 | 2025-12-07 | CLM-005 | EVT-005 | Clearance gap creates immediate risk. Cannot access SCIF. | N | Medium | Mr. Davis (KO)
REV-006 | 2025-12-28 | CLM-006 | EVT-006 | SLA breach pattern: 5 of 8 weeks exceeded. Not isolated. | Y | High | Mr. Jackson (QA)
REV-007 | 2026-01-03 | CLM-007 | EVT-007 | Content adequate but delivery format needs improvement. Minor. | Y | Low | MAJ Torres (COR)
REV-008 | 2026-01-19 | CLM-008 | EVT-008 | Coverage deficit is a quality risk. Cannot accept until remediated. | Y | Medium | Ms. Kim (Audit)
REV-009 | 2025-11-19 | CLM-009 | EVT-009 | On-call failure during Severity 1 is a critical performance issue. | Y | Medium | CPT Chen (ACOR)
REV-010 | 2026-01-08 | CLM-010 | EVT-010 | Backup failures create data loss risk. Corrective action required. | N | Low | Mr. Davis (KO)
REV-011 | 2026-01-15 | CLM-011 | EVT-011 | Dashboard gap acceptable during scheduled maintenance. No drift. | Y | Critical | Mr. Jackson (QA)
REV-012 | 2025-11-02 | CLM-012 | EVT-012 | Response time failure is critical. Incident playbook not followed. | Y | High | MAJ Torres (COR)
REV-013 | 2025-12-09 | CLM-013 | EVT-013 | Format non-conformance is correctable. Issue COR direction. | Y | Low | Ms. Kim (Audit)
REV-014 | 2025-11-30 | CLM-014 | EVT-014 | Outdated training creates operational risk. Immediate update required. | N | Low | CPT Chen (ACOR)
REV-015 | 2025-11-10 | CLM-015 | EVT-015 | Late delivery within tolerance (5 days). Issue verbal notice. | N | Low | Mr. Davis (KO)
REV-016 | 2026-01-07 | CLM-016 | EVT-016 | Drift confirmed: 3 of last 4 reports late. Pattern, not one-time. | Y | Medium | Mr. Jackson (QA)
REV-017 | 2026-01-23 | CLM-017 | EVT-017 | Security findings are valid Critical. Deliverable cannot be accepted. | N | Medium | MAJ Torres (COR)
REV-018 | 2025-12-03 | CLM-018 | EVT-018 | Uptime below threshold 2 consecutive months. Systemic issue. | N | Critical | Ms. Kim (Audit)
REV-019 | 2025-11-27 | CLM-019 | EVT-019 | Minor deviation. Verbal counseling sufficient. Monitor next 4 weeks. | N | Medium | CPT Chen (ACOR)
REV-020 | 2025-12-09 | CLM-020 | EVT-020 | Clearance gap creates immediate risk. Cannot access SCIF. | N | High | Mr. Davis (KO)

## Patches
PatchID | Date | ReviewID | ClaimID | Correction | Rationale | Approver | Status
PAT-001 | 2025-12-31 | REV-001 | CLM-001 | COR letter issued. Contractor to submit corrective action plan by April 15. | Review REV-001 identified drift requiring correction. See linked finding. | Ms. Patel (PM) | Applied
PAT-002 | 2026-01-01 | REV-002 | CLM-002 | Deliverable returned. Contractor to remediate 3 Critical findings and resubmit. | Review REV-002 identified drift requiring correction. See linked finding. | Mr. Davis (KO) | Pending
PAT-003 | 2025-12-06 | REV-003 | CLM-003 | Performance improvement plan required within 14 days. Next 2 months monitored. | Review REV-003 identified drift requiring correction. See linked finding. | COL Richardson (DPM) | Approved
PAT-004 | 2025-11-13 | REV-004 | CLM-004 | Verbal counseling documented in COR file. No formal action at this time. | Review REV-004 identified drift requiring correction. See linked finding. | Ms. Patel (PM) | Approved
PAT-005 | 2025-11-07 | REV-005 | CLM-005 | Contractor directed to resolve clearance gaps within 10 business days or replace personnel. | Review REV-005 identified drift requiring correction. See linked finding. | Ms. Patel (PM) | Applied
PAT-006 | 2026-01-14 | REV-006 | CLM-006 | Cure notice drafted. 10-day cure period. If not remediated, escalate to KO. | Review REV-006 identified drift requiring correction. See linked finding. | Mr. Davis (KO) | Approved
PAT-007 | 2026-01-19 | REV-007 | CLM-007 | COR direction issued: reformat Q2 deliverable per DI-MGMT-81466 template. | Review REV-007 identified drift requiring correction. See linked finding. | COL Richardson (DPM) | Approved
PAT-008 | 2025-11-05 | REV-008 | CLM-008 | Sprint 15 deliverable must demonstrate >80% coverage or will be rejected. | Review REV-008 identified drift requiring correction. See linked finding. | Ms. Patel (PM) | Pending
PAT-009 | 2026-02-03 | REV-009 | CLM-009 | Contractor to revise on-call procedures and provide updated roster within 7 days. | Review REV-009 identified drift requiring correction. See linked finding. | Ms. Patel (PM) | Applied
PAT-010 | 2025-11-12 | REV-010 | CLM-010 | Contractor to implement automated backup verification. Report daily for 30 days. | Review REV-010 identified drift requiring correction. See linked finding. | Mr. Davis (KO) | Approved
PAT-011 | 2025-11-13 | REV-011 | CLM-011 | No action required. Dashboard gap within acceptable maintenance window. | Review REV-011 identified drift requiring correction. See linked finding. | COL Richardson (DPM) | Pending
PAT-012 | 2025-12-17 | REV-012 | CLM-012 | Contractor to conduct incident response drill within 14 days. Report results. | Review REV-012 identified drift requiring correction. See linked finding. | Ms. Patel (PM) | Pending
PAT-013 | 2026-01-09 | REV-013 | CLM-013 | COR direction: update all documentation to current template within 30 days. | Review REV-013 identified drift requiring correction. See linked finding. | Ms. Patel (PM) | Approved
PAT-014 | 2025-12-10 | REV-014 | CLM-014 | Contractor to update all training materials to v3.0 within 21 days. | Review REV-014 identified drift requiring correction. See linked finding. | Mr. Davis (KO) | Applied
PAT-015 | 2026-01-06 | REV-015 | CLM-015 | Written notice issued. Next late delivery triggers formal cure notice. | Review REV-015 identified drift requiring correction. See linked finding. | COL Richardson (DPM) | Approved

## Apply
ApplyID | Date | PatchID | ClaimID | Action Taken | Evidence | Verified By
APL-001 | 2026-01-23 | PAT-001 | CLM-001 | CAP received April 14. Reviewed and accepted. April report delivered on time. Claim updated. | \\fileserver\TO-Evidence\APL-001_closeout.pdf | MAJ Torres (COR)
APL-002 | 2026-02-15 | PAT-002 | CLM-002 | Resubmission received. All 3 Critical findings remediated. Deliverable accepted. | \\fileserver\TO-Evidence\APL-002_closeout.pdf | Mr. Davis (KO)
APL-003 | 2026-01-27 | PAT-003 | CLM-003 | PIP submitted. March uptime measured at 99.1%. Monitoring continues. | \\fileserver\TO-Evidence\APL-003_closeout.pdf | CPT Chen (ACOR)
APL-004 | 2025-12-16 | PAT-004 | CLM-004 | Verbal counseling noted. Next 4 reports delivered on time. Issue closed. | \\fileserver\TO-Evidence\APL-004_closeout.pdf | CPT Chen (ACOR)
APL-005 | 2026-02-26 | PAT-005 | CLM-005 | 2 personnel replaced within 8 days. Clearance verification confirmed. Claim restored. | \\fileserver\TO-Evidence\APL-005_closeout.pdf | CPT Chen (ACOR)
APL-006 | 2025-12-09 | PAT-006 | CLM-006 | Cure notice issued. Help desk SLA met for 4 consecutive weeks after cure. Closed. | \\fileserver\TO-Evidence\APL-006_closeout.pdf | Mr. Jackson (QA)
APL-007 | 2025-11-27 | PAT-007 | CLM-007 | Q2 deliverable reformatted correctly. Accepted. Template compliance confirmed. | \\fileserver\TO-Evidence\APL-007_closeout.pdf | CPT Chen (ACOR)
APL-008 | 2025-12-30 | PAT-008 | CLM-008 | Sprint 15 code coverage: 84%. Threshold met. Deliverable accepted. | \\fileserver\TO-Evidence\APL-008_closeout.pdf | CPT Chen (ACOR)
APL-009 | 2026-01-06 | PAT-009 | CLM-009 | Revised on-call roster received. Drill conducted successfully. Verified operational. | \\fileserver\TO-Evidence\APL-009_closeout.pdf | CPT Chen (ACOR)
APL-010 | 2026-02-16 | PAT-010 | CLM-010 | Automated verification implemented. 30-day report shows 100% backup success. Closed. | \\fileserver\TO-Evidence\APL-010_closeout.pdf | Mr. Jackson (QA)