## Dashboard
CERPA v3 — OPERATIONAL DASHBOARD
VOLUME | 30 | 25 |  | 20 |  | 15 | 10
| Claims | Events |  | Reviews |  | Patches | Applied
DRIFT |  |  |  |  | SEVERITY
Drift Y | 11 | Dev Y | 17 |  | Critical | 3
Drift N | 9 | Dev N | 8 |  | High | 4
Rate | 55% | Dev Rate | 68% |  | Medium | 6
[5 empty] | Low | 7
RISK SCORE |  | STATUS |  |  | COVERAGE
High Risk (>60) | 6 | Open | 18 |  | Event Cov | 83.33%
Medium Risk (30-60) | 20 | Under Review | 4 |  | Review Cov | 80%
Low Risk (0-30) | 4 | Patched | 4 |  | Patch Rate | 136.4%
Avg Risk Score | 51.7538 | Closed | 4 |  | Apply Rate | 66.67%
AGING |  | CYCLE TIME |  |  | CHANGELOG
>30 days | 26 | Evt→Rev (days) | 31.45 |  | Total Edits | 15
>60 days | 26 | Pending>14d | 4
>90 days | 26 | Completion | 33.33%
Avg Open | 155.1538
v3 FEATURES: Structured Tables ¦ Risk Scoring Engine ¦ COR Weekly Report ¦ Changelog ¦ Data Validation ¦ INDEX/MATCH Auto-Pull ¦ Overdue Detection

## Claims
ClaimID | Date | Owner | Description | Source | Status | LinkedEventIDs | DaysOpen | DriftCount | MaxSeverity | PatchStatus | RiskScore
CLM-001 | 2025-10-11 | MAJ Torres (COR) | Monthly status report by 5th business day | SOW 3.1 | Open | EVT-001 | 152 | 0 | 4 | Applied | 50
CLM-002 | 2025-10-01 | CPT Chen (ACOR) | Software deliverables pass security scan before acceptance | SOW 3.2 | Closed | EVT-002 | — | 1 | 1 | Pending | 0
CLM-003 | 2025-10-05 | Mr. Davis (KO) | Maintain 98% system uptime during core hours | SOW 4.1 | Open | EVT-003 | 158 | 1 | 3 | Approved | 59.8
CLM-004 | 2025-10-04 | Ms. Patel (PM) | Weekly staffing report due Monday by 1200 | SOW 5.3 | Open | EVT-004 | 159 | 1 | 1 | Approved | 47.3
CLM-005 | 2025-10-12 | SSG Miller (QA) | All personnel hold TS/SCI clearance | CDRL A001 | Open | EVT-005 | 151 | 0 | 2 | Applied | 37.5
CLM-006 | 2025-10-11 | MAJ Torres (COR) | Help desk response within 15 min during business hours | CDRL A003 | Closed | EVT-006 | — | 1 | 3 | Approved | 0
CLM-007 | 2025-10-15 | CPT Chen (ACOR) | Quarterly program review by 10th of quarter | CDRL A005 | Patched | EVT-007 | 148 | 1 | 1 | Approved | 47.3
CLM-008 | 2025-10-02 | Mr. Davis (KO) | Code commits include >80% unit test coverage | PWS 3.2.1 | Patched | EVT-008 | 161 | 1 | 2 | Pending | 63.5
CLM-009 | 2025-10-07 | Ms. Patel (PM) | 24/7 on-call support for critical systems | PWS 4.1.3 | Open | EVT-009 | 156 | 1 | 2 | Applied | 43.5
CLM-010 | 2025-10-01 | SSG Miller (QA) | Nightly backup with weekly verification log | QASP 2 | Open | EVT-010 | 162 | 0 | 1 | Approved | 41.3
CLM-011 | 2025-10-04 | MAJ Torres (COR) | Network monitoring dashboard real-time 5-min refresh | QASP 4 | Open | EVT-011 | 159 | 1 | 4 | Pending | 76
CLM-012 | 2025-10-09 | CPT Chen (ACOR) | Incident response within 30 min of detection | TO Mod 001 | Patched | EVT-012 | 154 | 1 | 3 | Pending | 69.8
CLM-013 | 2025-10-01 | Mr. Davis (KO) | Documentation per DI-MGMT-81466 | TO Mod 003 | Patched | EVT-013 | 162 | 1 | 1 | Approved | 47.3
CLM-014 | 2025-10-04 | Ms. Patel (PM) | Training materials updated within 30 days of change | Policy 24-01 | Closed | EVT-014 | — | 0 | 1 | Applied | 0
CLM-015 | 2025-10-11 | SSG Miller (QA) | Transition plan 90 days before PoP end | COR Dir 25-001 | Closed | EVT-015 | — | 0 | 1 | Approved | 0
CLM-016 | 2025-10-09 | MAJ Torres (COR) | Comply with NIST 800-171 | SOW 3.1 | Under Review | EVT-016 | 154 | 1 | 2 | None | 63.5
CLM-017 | 2025-10-04 | CPT Chen (ACOR) | Configuration management plan current | SOW 3.2 | Under Review | EVT-017 | 159 | 0 | 2 | None | 57.5
CLM-018 | 2025-10-10 | Mr. Davis (KO) | Critical CVE patches within 72 hours | SOW 4.1 | Open | EVT-018 | 153 | 0 | 4 | None | 70
CLM-019 | 2025-10-13 | Ms. Patel (PM) | Travel requires prior COR written approval | SOW 5.3 | Open | EVT-019 | 150 | 0 | 2 | None | 57.5
CLM-020 | 2025-10-13 | SSG Miller (QA) | Monthly financial report with burn-rate by 10th | CDRL A001 | Open | EVT-020 | 150 | 0 | 3 | None | 63.8
CLM-021 | 2025-10-12 | MAJ Torres (COR) | Risk register reviewed at each program review | CDRL A003 | Under Review | EVT-021 | 151 | 0 | 0 | None | 45
CLM-022 | 2025-10-06 | CPT Chen (ACOR) | Key personnel changes require 30-day notice | CDRL A005 | Open | EVT-022 | 157 | 0 | 0 | None | 45
CLM-023 | 2025-10-03 | Mr. Davis (KO) | GFE tracked in property log | PWS 3.2.1 | Open | EVT-023 | 160 | 0 | 0 | None | 45
CLM-024 | 2025-10-13 | Ms. Patel (PM) | Test plan approved before testing begins | PWS 4.1.3 | Open | EVT-024 | 150 | 0 | 0 | None | 45
CLM-025 | 2025-10-02 | SSG Miller (QA) | Final delivery acceptance within 10 business days | QASP 2 | Open | EVT-025 | 161 | 0 | 0 | None | 45
CLM-026 | 2025-10-07 | MAJ Torres (COR) | Maintain ISO 27001 certification throughout PoP | QASP 4 | Open |  | 156 | 0 | 0 | None | 45
CLM-027 | 2025-10-06 | CPT Chen (ACOR) | Sub-contractor performance reported quarterly | TO Mod 001 | Open |  | 157 | 0 | 0 | None | 45
CLM-028 | 2025-10-10 | Mr. Davis (KO) | EVM reports delivered monthly per CDRL | TO Mod 003 | Open |  | 153 | 0 | 0 | None | 45
CLM-029 | 2025-10-13 | Ms. Patel (PM) | Access control logs reviewed weekly | Policy 24-01 | Open |  | 150 | 0 | 0 | None | 45
CLM-030 | 2025-10-12 | SSG Miller (QA) | Lessons learned within 30 days of milestone | COR Dir 25-001 | Under Review |  | 151 | 0 | 0 | None | 45
Formulas:
DaysOpen = IF([Status]="Closed","—",TODAY()-[Date])

## Events
EventID | Date | ClaimID | Observer | WhatHappened | Evidence | Deviation | ClaimDesc_auto | ClaimSource_auto
EVT-001 | 2025-12-23 | CLM-001 | MAJ Torres (COR) | March report delivered 12th business day — 7 days late | \\server\Evidence\EVT-001.pdf | N | Monthly status report by 5th business day | SOW 3.1
EVT-002 | 2025-10-26 | CLM-002 | SSG Miller (QA) | Security scan: 3 critical findings | \\server\Evidence\EVT-002.pdf | Y | Software deliverables pass security scan before acceptance | SOW 3.2
EVT-003 | 2025-12-01 | CLM-003 | SSG Miller (QA) | Feb uptime 94.2% — below 98% | \\server\Evidence\EVT-003.pdf | Y | Maintain 98% system uptime during core hours | SOW 4.1
EVT-004 | 2025-10-24 | CLM-004 | MAJ Torres (COR) | Staffing report Monday at 1430 — 2.5 hrs late | \\server\Evidence\EVT-004.pdf | Y | Weekly staffing report due Monday by 1200 | SOW 5.3
EVT-005 | 2025-11-22 | CLM-005 | MAJ Torres (COR) | 2 of 14 staff have expired clearances | \\server\Evidence\EVT-005.pdf | Y | All personnel hold TS/SCI clearance | CDRL A001
EVT-006 | 2025-10-28 | CLM-006 | Ms. Patel (PM) | Help desk avg response: 22 min — exceeds SLA | \\server\Evidence\EVT-006.pdf | Y | Help desk response within 15 min during business hours | CDRL A003
EVT-007 | 2025-12-13 | CLM-007 | Mr. Davis (KO) | Q1 review on time; content reviewed | \\server\Evidence\EVT-007.pdf | Y | Quarterly program review by 10th of quarter | CDRL A005
EVT-008 | 2025-12-02 | CLM-008 | Mr. Davis (KO) | Code coverage 71% on Sprint 14 | \\server\Evidence\EVT-008.pdf | Y | Code commits include >80% unit test coverage | PWS 3.2.1
EVT-009 | 2025-11-19 | CLM-009 | MAJ Torres (COR) | On-call unreachable 45 min during Sev1 | \\server\Evidence\EVT-009.pdf | N | 24/7 on-call support for critical systems | PWS 4.1.3
EVT-010 | 2025-11-06 | CLM-010 | SSG Miller (QA) | 3 failed backups week of 3/15 | \\server\Evidence\EVT-010.pdf | Y | Nightly backup with weekly verification log | QASP 2
EVT-011 | 2025-11-05 | CLM-011 | Ms. Patel (PM) | Dashboard 15-min gap during maintenance | \\server\Evidence\EVT-011.pdf | N | Network monitoring dashboard real-time 5-min refresh | QASP 4
EVT-012 | 2025-11-19 | CLM-012 | SSG Miller (QA) | Incident response: 47 min for P1 outage | \\server\Evidence\EVT-012.pdf | Y | Incident response within 30 min of detection | TO Mod 001
EVT-013 | 2025-11-26 | CLM-013 | MAJ Torres (COR) | Doc format non-conformant to template | \\server\Evidence\EVT-013.pdf | Y | Documentation per DI-MGMT-81466 | TO Mod 003
EVT-014 | 2025-10-20 | CLM-014 | Mr. Davis (KO) | Training references deprecated v2.1 vs v3.0 | \\server\Evidence\EVT-014.pdf | N | Training materials updated within 30 days of change | Policy 24-01
EVT-015 | 2025-11-19 | CLM-015 | MAJ Torres (COR) | Transition plan submitted day 85 — 5 days late | \\server\Evidence\EVT-015.pdf | Y | Transition plan 90 days before PoP end | COR Dir 25-001
EVT-016 | 2025-12-27 | CLM-016 | Mr. Davis (KO) | NIST self-assessment 87/110 — 3 POAMs | \\server\Evidence\EVT-016.pdf | Y | Comply with NIST 800-171 | SOW 3.1
EVT-017 | 2025-12-18 | CLM-017 | Ms. Patel (PM) | CM plan 6 months stale | \\server\Evidence\EVT-017.pdf | N | Configuration management plan current | SOW 3.2
EVT-018 | 2025-11-03 | CLM-018 | Mr. Davis (KO) | CVE patches applied in 96 hrs — 24 hrs over | \\server\Evidence\EVT-018.pdf | Y | Critical CVE patches within 72 hours | SOW 4.1
EVT-019 | 2025-11-16 | CLM-019 | SSG Miller (QA) | Travel without COR approval | \\server\Evidence\EVT-019.pdf | N | Travel requires prior COR written approval | SOW 5.3
EVT-020 | 2025-11-18 | CLM-020 | SSG Miller (QA) | Financial report 15th — 5 days late, burn rate missing | \\server\Evidence\EVT-020.pdf | N | Monthly financial report with burn-rate by 10th | CDRL A001
EVT-021 | 2025-12-29 | CLM-021 | Ms. Patel (PM) | Sub-contractor report 2 weeks overdue | \\server\Evidence\EVT-021.pdf | Y | Risk register reviewed at each program review | CDRL A003
EVT-022 | 2025-11-13 | CLM-022 | CPT Chen (ACOR) | EVM CPI 0.87 — below 0.95 | \\server\Evidence\EVT-022.pdf | N | Key personnel changes require 30-day notice | CDRL A005
EVT-023 | 2025-12-18 | CLM-023 | MAJ Torres (COR) | Access logs not reviewed 3 weeks | \\server\Evidence\EVT-023.pdf | Y | GFE tracked in property log | PWS 3.2.1
EVT-024 | 2025-10-30 | CLM-024 | CPT Chen (ACOR) | Test plan missing Module C scenarios | \\server\Evidence\EVT-024.pdf | Y | Test plan approved before testing begins | PWS 4.1.3
EVT-025 | 2025-12-09 | CLM-025 | SSG Miller (QA) | GFE log: 3 items unaccounted for | \\server\Evidence\EVT-025.pdf | Y | Final delivery acceptance within 10 business days | QASP 2

## Reviews
ReviewID | Date | ClaimID | EventID | Finding | DriftDetected | Severity | Reviewer | ClaimDesc_auto | DaysSinceEvent
REV-001 | 2025-12-19 | CLM-001 | EVT-001 | 3 of 4 reports late. Pattern. | N | Critical | Mr. Jackson (QA) | Monthly status report by 5th business day | -4
REV-002 | 2026-01-06 | CLM-002 | EVT-002 | Critical findings. Cannot accept. | Y | Low | MAJ Torres (COR) | Software deliverables pass security scan before acceptance | 72
REV-003 | 2026-01-26 | CLM-003 | EVT-003 | Uptime below 2 months. Systemic. | Y | High | Ms. Kim (Audit) | Maintain 98% system uptime during core hours | 56
REV-004 | 2026-01-21 | CLM-004 | EVT-004 | Minor. Verbal counseling. Monitor 4 weeks. | Y | Low | CPT Chen (ACOR) | Weekly staffing report due Monday by 1200 | 89
REV-005 | 2025-12-07 | CLM-005 | EVT-005 | Clearance gap. Cannot access SCIF. | N | Medium | Mr. Davis (KO) | All personnel hold TS/SCI clearance | 15
REV-006 | 2025-12-28 | CLM-006 | EVT-006 | SLA breach 5 of 8 weeks. Not isolated. | Y | High | Mr. Jackson (QA) | Help desk response within 15 min during business hours | 61
REV-007 | 2026-01-03 | CLM-007 | EVT-007 | Content ok. Format needs work. Minor. | Y | Low | MAJ Torres (COR) | Quarterly program review by 10th of quarter | 21
REV-008 | 2026-01-19 | CLM-008 | EVT-008 | Coverage deficit. Quality risk. | Y | Medium | Ms. Kim (Audit) | Code commits include >80% unit test coverage | 48
REV-009 | 2025-11-19 | CLM-009 | EVT-009 | On-call failure during Sev1. Critical. | Y | Medium | CPT Chen (ACOR) | 24/7 on-call support for critical systems | 0
REV-010 | 2026-01-08 | CLM-010 | EVT-010 | Backup failures. Data loss risk. | N | Low | Mr. Davis (KO) | Nightly backup with weekly verification log | 63
REV-011 | 2026-01-15 | CLM-011 | EVT-011 | Gap acceptable during maintenance. | Y | Critical | Mr. Jackson (QA) | Network monitoring dashboard real-time 5-min refresh | 71
REV-012 | 2025-11-02 | CLM-012 | EVT-012 | Response time critical. Playbook not followed. | Y | High | MAJ Torres (COR) | Incident response within 30 min of detection | -17
REV-013 | 2025-12-09 | CLM-013 | EVT-013 | Format non-conformance. Correctable. | Y | Low | Ms. Kim (Audit) | Documentation per DI-MGMT-81466 | 13
REV-014 | 2025-11-30 | CLM-014 | EVT-014 | Outdated training. Immediate update needed. | N | Low | CPT Chen (ACOR) | Training materials updated within 30 days of change | 41
REV-015 | 2025-11-10 | CLM-015 | EVT-015 | Late within tolerance. Verbal notice. | N | Low | Mr. Davis (KO) | Transition plan 90 days before PoP end | -9
REV-016 | 2026-01-07 | CLM-016 | EVT-016 | NIST gap. Formal POAM required. | Y | Medium | Mr. Jackson (QA) | Comply with NIST 800-171 | 11
REV-017 | 2026-01-23 | CLM-017 | EVT-017 | CM staleness. Config risk. | N | Medium | MAJ Torres (COR) | Configuration management plan current | 36
REV-018 | 2025-12-03 | CLM-018 | EVT-018 | CVE delay. Security risk. Escalate. | N | Critical | Ms. Kim (Audit) | Critical CVE patches within 72 hours | 30
REV-019 | 2025-11-27 | CLM-019 | EVT-019 | Unauthorized travel. Compliance violation. | N | Medium | CPT Chen (ACOR) | Travel requires prior COR written approval | 11
REV-020 | 2025-12-09 | CLM-020 | EVT-020 | Financial delay impairs visibility. | N | High | Mr. Davis (KO) | Monthly financial report with burn-rate by 10th | 21

## Patches
PatchID | Date | ReviewID | ClaimID | Correction | Rationale | Approver | Status | ClaimDesc_auto | ReviewFinding_auto
PAT-001 | 2025-12-31 | REV-001 | CLM-001 | COR letter. CAP due April 15. | Review REV-001 drift requiring correction. | Ms. Patel (PM) | Applied | Monthly status report by 5th business day | 3 of 4 reports late. Pattern.
PAT-002 | 2026-01-01 | REV-002 | CLM-002 | Deliverable returned. Remediate and resubmit. | Review REV-002 drift requiring correction. | Mr. Davis (KO) | Pending | Software deliverables pass security scan before acceptance | Critical findings. Cannot accept.
PAT-003 | 2025-12-06 | REV-003 | CLM-003 | PIP required 14 days. Monitor 2 months. | Review REV-003 drift requiring correction. | COL Richardson (DPM) | Approved | Maintain 98% system uptime during core hours | Uptime below 2 months. Systemic.
PAT-004 | 2025-11-13 | REV-004 | CLM-004 | Verbal counseling documented. | Review REV-004 drift requiring correction. | Ms. Patel (PM) | Approved | Weekly staffing report due Monday by 1200 | Minor. Verbal counseling. Monitor 4 weeks.
PAT-005 | 2025-11-07 | REV-005 | CLM-005 | Resolve clearances 10 days or replace. | Review REV-005 drift requiring correction. | Mr. Davis (KO) | Applied | All personnel hold TS/SCI clearance | Clearance gap. Cannot access SCIF.
PAT-006 | 2026-01-14 | REV-006 | CLM-006 | Cure notice. 10-day cure period. | Review REV-006 drift requiring correction. | COL Richardson (DPM) | Approved | Help desk response within 15 min during business hours | SLA breach 5 of 8 weeks. Not isolated.
PAT-007 | 2026-01-19 | REV-007 | CLM-007 | COR direction: reformat per template. | Review REV-007 drift requiring correction. | Ms. Patel (PM) | Approved | Quarterly program review by 10th of quarter | Content ok. Format needs work. Minor.
PAT-008 | 2025-11-05 | REV-008 | CLM-008 | Sprint 15 must show >80% or reject. | Review REV-008 drift requiring correction. | Mr. Davis (KO) | Pending | Code commits include >80% unit test coverage | Coverage deficit. Quality risk.
PAT-009 | 2026-02-03 | REV-009 | CLM-009 | Revise on-call procedures. Roster in 7 days. | Review REV-009 drift requiring correction. | COL Richardson (DPM) | Applied | 24/7 on-call support for critical systems | On-call failure during Sev1. Critical.
PAT-010 | 2025-11-12 | REV-010 | CLM-010 | Implement automated backup verify. Daily 30 days. | Review REV-010 drift requiring correction. | Ms. Patel (PM) | Approved | Nightly backup with weekly verification log | Backup failures. Data loss risk.
PAT-011 | 2025-11-13 | REV-011 | CLM-011 | No action. Within maintenance window. | Review REV-011 drift requiring correction. | Mr. Davis (KO) | Pending | Network monitoring dashboard real-time 5-min refresh | Gap acceptable during maintenance.
PAT-012 | 2025-12-17 | REV-012 | CLM-012 | Incident response drill 14 days. | Review REV-012 drift requiring correction. | COL Richardson (DPM) | Pending | Incident response within 30 min of detection | Response time critical. Playbook not followed.
PAT-013 | 2026-01-09 | REV-013 | CLM-013 | Update all docs to current template 30 days. | Review REV-013 drift requiring correction. | Ms. Patel (PM) | Approved | Documentation per DI-MGMT-81466 | Format non-conformance. Correctable.
PAT-014 | 2025-12-10 | REV-014 | CLM-014 | Update training to v3.0 in 21 days. | Review REV-014 drift requiring correction. | Mr. Davis (KO) | Applied | Training materials updated within 30 days of change | Outdated training. Immediate update needed.
PAT-015 | 2026-01-06 | REV-015 | CLM-015 | Written notice. Next late triggers cure. | Review REV-015 drift requiring correction. | COL Richardson (DPM) | Approved | Transition plan 90 days before PoP end | Late within tolerance. Verbal notice.

## Apply
ApplyID | Date | PatchID | ClaimID | ActionTaken | Evidence | VerifiedBy | ClaimDesc_auto | PatchCorrection_auto
APL-001 | 2026-01-23 | PAT-001 | CLM-001 | CAP received. April report on time. Claim updated. | \\server\Evidence\APL-001_close.pdf | MAJ Torres (COR) | Monthly status report by 5th business day | COR letter. CAP due April 15.
APL-002 | 2026-02-15 | PAT-002 | CLM-002 | Resubmission. All 3 Critical fixed. Accepted. | \\server\Evidence\APL-002_close.pdf | Mr. Davis (KO) | Software deliverables pass security scan before acceptance | Deliverable returned. Remediate and resubmit.
APL-003 | 2026-01-27 | PAT-003 | CLM-003 | PIP submitted. March uptime 99.1%. Monitoring. | \\server\Evidence\APL-003_close.pdf | CPT Chen (ACOR) | Maintain 98% system uptime during core hours | PIP required 14 days. Monitor 2 months.
APL-004 | 2025-12-16 | PAT-004 | CLM-004 | Next 4 reports on time. Closed. | \\server\Evidence\APL-004_close.pdf | CPT Chen (ACOR) | Weekly staffing report due Monday by 1200 | Verbal counseling documented.
APL-005 | 2026-02-26 | PAT-005 | CLM-005 | 2 personnel replaced 8 days. Verified. | \\server\Evidence\APL-005_close.pdf | CPT Chen (ACOR) | All personnel hold TS/SCI clearance | Resolve clearances 10 days or replace.
APL-006 | 2025-12-09 | PAT-006 | CLM-006 | SLA met 4 weeks. Closed. | \\server\Evidence\APL-006_close.pdf | Mr. Jackson (QA) | Help desk response within 15 min during business hours | Cure notice. 10-day cure period.
APL-007 | 2025-11-27 | PAT-007 | CLM-007 | Reformatted correctly. Accepted. | \\server\Evidence\APL-007_close.pdf | CPT Chen (ACOR) | Quarterly program review by 10th of quarter | COR direction: reformat per template.
APL-008 | 2025-12-30 | PAT-008 | CLM-008 | Sprint 15: 84% coverage. Accepted. | \\server\Evidence\APL-008_close.pdf | CPT Chen (ACOR) | Code commits include >80% unit test coverage | Sprint 15 must show >80% or reject.
APL-009 | 2026-01-06 | PAT-009 | CLM-009 | Revised roster. Drill successful. | \\server\Evidence\APL-009_close.pdf | CPT Chen (ACOR) | 24/7 on-call support for critical systems | Revise on-call procedures. Roster in 7 days.
APL-010 | 2026-02-16 | PAT-010 | CLM-010 | Auto verify live. 100% success 30 days. Closed. | \\server\Evidence\APL-010_close.pdf | Mr. Jackson (QA) | Nightly backup with weekly verification log | Implement automated backup verify. Daily 30 days.

## Changelog
EntryNo | Timestamp | User | Tab | RecordID | Field | OldValue | NewValue | Reason
1 | 2025-10-15 09:14 | MAJ Torres | Claims | CLM-003 | Status | Open | Under Review | Uptime drift detected — initiating review
2 | 2025-10-15 09:22 | MAJ Torres | Events | EVT-003 | Deviation | N | Y | Feb uptime 94.2% confirmed below threshold
3 | 2025-10-18 14:30 | Mr. Jackson | Reviews | REV-003 | Severity | Medium | High | Upgraded: 2 consecutive months below threshold
4 | 2025-10-22 10:45 | Ms. Patel | Patches | PAT-003 | Status | Pending | Approved | PIP approved by PM. Monitoring begins.
5 | 2025-11-01 08:00 | CPT Chen | Patches | PAT-003 | Status | Approved | Applied | PIP applied. March uptime monitoring started.
6 | 2025-11-05 11:15 | MAJ Torres | Claims | CLM-003 | Status | Under Review | Patched | PIP in effect. Awaiting 2-month observation.
7 | 2025-11-12 16:00 | Mr. Davis | Claims | CLM-019 | Status | Open | Under Review | Unauthorized travel discovered in expense review
8 | 2025-11-13 09:00 | Ms. Kim | Reviews | REV-019 | DriftDetected | N | Y | Travel violation confirmed. Compliance breach.
9 | 2025-11-15 14:20 | Mr. Davis | Patches | PAT-015 | Correction | — | Written notice + counseling | KO directed formal written notice to contractor
10 | 2025-11-20 08:30 | MAJ Torres | Events | EVT-020 | Evidence | — | \\server\EVT-020.pdf | Late financial report evidence package attached
11 | 2025-12-01 09:00 | CPT Chen | Claims | CLM-001 | Status | Open | Patched | CAP accepted. April report on time.
12 | 2025-12-05 10:15 | SSG Miller | Claims | CLM-008 | Status | Open | Under Review | Sprint 14 coverage at 71%. Below 80% threshold.
13 | 2025-12-10 13:40 | Mr. Jackson | Reviews | REV-008 | Severity | Low | Medium | Second sprint below coverage. Pattern emerging.
14 | 2025-12-15 11:00 | Ms. Patel | Patches | PAT-008 | Status | Pending | Approved | Sprint 15 must demonstrate >80% or reject.
15 | 2025-12-20 16:30 | MAJ Torres | Apply | APL-008 | ActionTaken | — | Sprint 15: 84%. Accepted. | Coverage threshold met. Deliverable accepted.
AUTO-LOGGING SETUP
To enable automatic change logging, save this workbook as .xlsm and add the following VBA macro:
1. Press Alt+F11 to open the VBA Editor
2. In the Project Explorer, double-click 'ThisWorkbook'
3. Paste the Workbook_SheetChange event handler (provided separately)
4. The macro will auto-log: timestamp, username, tab name, cell address, old value, new value
5. Until VBA is enabled, log changes manually by adding rows to this tab
FORMAT: EntryNo (sequential) ¦ Timestamp ¦ User ¦ Tab ¦ RecordID ¦ Field ¦ Old→New ¦ Reason

## COR Weekly Report
COR WEEKLY STATUS REPORT — AUTO-GENERATED FROM CERPA WORKBOOK
Report Date: | 2026-03-12
1. VOLUME SUMMARY
Total Claims | 30
Total Events | 25
Total Reviews | 20
Total Patches | 15
Total Applied | 10
2. OPEN ISSUES & OVERDUE
Claims Open (not Closed) | 26
Claims Open > 30 days | 26
Drifts Detected (unresolved) | 11
Patches Pending | 4
Patches Pending > 14 days | 4
Events with Deviation | 17
3. TOP 5 RISK CLAIMS (BY RISK SCORE)
ClaimID | Risk Score | Description | Status | Drift Count
CLM-011 | 76 | Network monitoring dashboard real-time 5-min refresh | Open | 1
CLM-018 | 70 | Critical CVE patches within 72 hours | Open | 0
CLM-012 | 69.8 | Incident response within 30 min of detection | Patched | 1
CLM-020 | 63.8 | Monthly financial report with burn-rate by 10th | Open | 0
CLM-008 | 63.5 | Code commits include >80% unit test coverage | Patched | 1
4. LOOP HEALTH
Event Coverage (Events/Claims) | 83.33%
Review Coverage (Reviews/Events) | 80%
Patch Rate (Patches/Drifts) | 136.4%
Completion Rate (Apply/Claims) | 33.33%
Drift Rate | 55%
Avg Days Open (non-closed) | 155.1538
Avg Risk Score (non-closed) | 51.7538
This report auto-calculates from the five CERPA tabs. Print to PDF for weekly COR briefing. Ctrl+Shift+F9 to refresh.