## Dashboard
CERPA WORKBOOK — OPERATIONAL DASHBOARD
30 |  | 25 |  | 20 | 15 |  | 10
Total Claims |  | Total Events |  | Total Reviews | Total Patches |  | Applied
DRIFT & DEVIATION |  |  | PATCH STATUS |  | SEVERITY |  |  | CLAIM STATUS
Drift Y | 11 |  | Applied | 4 | Critical | 3 |  | Open | 18
Drift N | 9 |  | Approved | 7 | High | 4 |  | Under Review | 4
Drift Rate | 55% |  | Pending | 4 | Medium | 6 |  | Patched | 4
Events Deviated | 14 |  |  |  | Low | 7 |  | Closed | 4
Events OK | 11
Deviation Rate | 56%
CYCLE TIME METRICS
Avg Event→Review |  | 31.45 |  | Avg Review→Patch | -5.7333 |  | Avg Patch→Apply |  | 29.8
Max Event→Review |  | 89 |  | Max Review→Patch | 76 |  | Max Patch→Apply |  | 111
COVERAGE RATIOS
Event Coverage | Claims with Events |  |  | 83.33%
Review Coverage | Events reviewed |  |  | 80%
Patch Rate | Reviews patched |  |  | 75%
Closure Rate | Patches applied |  |  | 26.67%
Full Loop | Claims→Apply |  |  | 33.33%
AGING ANALYSIS
Claims Open >30 days |  |  |  | 18
Claims Open 14-30 days |  |  |  | 0
Drift Reviews >14d old |  |  |  | 7
Pending Patches |  |  |  | 4
HOW TO USE
1. CLAIMS: Register decisions. Days Open auto-calculates. Red >30d, Yellow >14d.
2. EVENTS: Select ClaimID from dropdown. Description + Source auto-pull from Claims.
3. REVIEWS: Select ClaimID + EventID from dropdowns. Days Since Event auto-calculates.
4. PATCHES: Select ReviewID + ClaimID. Finding auto-pulls. Days to Patch auto-calculates.
5. APPLY: Select PatchID + ClaimID. Correction auto-pulls. Days to Apply auto-calculates.
6. AUDIT: Filter any tab by ClaimID → export to PDF = evidence package.
7. OVERDUE: Red flags auto-appear: Claims >30d, Drift >14d, Pending Patches >7d.
8. UPGRADE: When you outgrow Excel → SharePoint List → Power Apps → GRC. Every row migrates.

## Claims
ClaimID | Date | Owner | Description | Source | Status | LinkedEventIDs | Days Open
CLM-001 | 2025-10-11 | MAJ Torres (COR) | Contractor shall deliver monthly status report by 5th business day | SOW 3.1 | Open | EVT-001 | 152
CLM-002 | 2025-10-01 | CPT Chen (ACOR) | All software deliverables shall pass security scan before acceptance | SOW 3.2 | Closed | EVT-002 | —
CLM-003 | 2025-10-05 | Mr. Davis (KO) | Contractor shall maintain 98% system uptime during core hours | SOW 4.1 | Open | EVT-003 | 158
CLM-004 | 2025-10-04 | Ms. Patel (PM) | Weekly staffing report due every Monday by 1200 | SOW 5.3 | Open | EVT-004 | 159
CLM-005 | 2025-10-12 | SSG Miller (QA) | All personnel shall hold current security clearance at TS/SCI | CDRL A001 | Open | EVT-005 | 151
CLM-006 | 2025-10-11 | MAJ Torres (COR) | Help desk response time shall not exceed 15 minutes | CDRL A003 | Closed | EVT-006 | —
CLM-007 | 2025-10-15 | CPT Chen (ACOR) | Quarterly program review briefing by 10th of quarter | CDRL A005 | Patched | EVT-007 | 148
CLM-008 | 2025-10-02 | Mr. Davis (KO) | All code commits shall include unit test coverage above 80% | PWS 3.2.1 | Patched | EVT-008 | 161
CLM-009 | 2025-10-07 | Ms. Patel (PM) | Contractor shall provide 24/7 on-call support for critical systems | PWS 4.1.3 | Open | EVT-009 | 156
CLM-010 | 2025-10-01 | SSG Miller (QA) | Data backup completed nightly with verification log weekly | QASP 2 | Open | EVT-010 | 162
CLM-011 | 2025-10-04 | MAJ Torres (COR) | Network monitoring dashboard updated real-time 5-min refresh | QASP 4 | Open | EVT-011 | 159
CLM-012 | 2025-10-09 | CPT Chen (ACOR) | Incident response initiated within 30 minutes of detection | TO Mod 001 | Patched | EVT-012 | 154
CLM-013 | 2025-10-01 | Mr. Davis (KO) | All documentation per DI-MGMT-81466 | TO Mod 003 | Patched | EVT-013 | 162
CLM-014 | 2025-10-04 | Ms. Patel (PM) | Training materials updated within 30 days of system change | Policy 24-01 | Closed | EVT-014 | —
CLM-015 | 2025-10-11 | SSG Miller (QA) | Transition plan delivered 90 days before PoP end | COR Dir 25-001 | Closed | EVT-015 | —
CLM-016 | 2025-10-09 | MAJ Torres (COR) | Comply with NIST 800-171 requirements | SOW 3.1 | Under Review | EVT-016 | 154
CLM-017 | 2025-10-04 | CPT Chen (ACOR) | Configuration management plan maintained and current | SOW 3.2 | Under Review | EVT-017 | 159
CLM-018 | 2025-10-10 | Mr. Davis (KO) | System patches applied within 72 hours for critical CVEs | SOW 4.1 | Open | EVT-018 | 153
CLM-019 | 2025-10-13 | Ms. Patel (PM) | All travel requires prior written COR approval | SOW 5.3 | Open | EVT-019 | 150
CLM-020 | 2025-10-13 | SSG Miller (QA) | Monthly financial report with cost/burn-rate by 10th | CDRL A001 | Open | EVT-020 | 150
CLM-021 | 2025-10-12 | MAJ Torres (COR) | Risk register maintained and reviewed at each program review | CDRL A003 | Under Review | EVT-021 | 151
CLM-022 | 2025-10-06 | CPT Chen (ACOR) | Key personnel changes require 30-day advance notice | CDRL A005 | Open | EVT-022 | 157
CLM-023 | 2025-10-03 | Mr. Davis (KO) | All GFE tracked in property log | PWS 3.2.1 | Open | EVT-023 | 160
CLM-024 | 2025-10-13 | Ms. Patel (PM) | Test plan approved before system testing begins | PWS 4.1.3 | Open | EVT-024 | 150
CLM-025 | 2025-10-02 | SSG Miller (QA) | Final delivery acceptance within 10 business days | QASP 2 | Open | EVT-025 | 161
CLM-026 | 2025-10-07 | MAJ Torres (COR) | Maintain ISO 27001 certification throughout PoP | QASP 4 | Open |  | 156
CLM-027 | 2025-10-06 | CPT Chen (ACOR) | Sub-contractor performance reported quarterly | TO Mod 001 | Open |  | 157
CLM-028 | 2025-10-10 | Mr. Davis (KO) | EVM reports delivered monthly per CDRL | TO Mod 003 | Open |  | 153
CLM-029 | 2025-10-13 | Ms. Patel (PM) | Access control logs reviewed weekly | Policy 24-01 | Open |  | 150
CLM-030 | 2025-10-12 | SSG Miller (QA) | Lessons learned report within 30 days of milestone | COR Dir 25-001 | Under Review |  | 151
Formulas:
Days Open = IF([Status]="Closed","—",TODAY()-[Date])

## Events
EventID | Date | ClaimID | Observer | What Happened | Evidence | Deviation | ⬅ Claim Desc (auto) | ⬅ Source (auto)
EVT-001 | 2025-12-23 | CLM-001 | Ms. Patel (PM) | March status report delivered 12th business day — 7 days late | \\fileserver\TO-Evidence\EVT-001.pdf | Y | Contractor shall deliver monthly status report by 5th business day | SOW 3.1
EVT-002 | 2025-10-26 | CLM-002 | Mr. Davis (KO) | Security scan: 3 critical findings identified | \\fileserver\TO-Evidence\EVT-002.pdf | N | All software deliverables shall pass security scan before acceptance | SOW 3.2
EVT-003 | 2025-12-01 | CLM-003 | CPT Chen (ACOR) | System uptime 94.2% February — below 98% | \\fileserver\TO-Evidence\EVT-003.pdf | N | Contractor shall maintain 98% system uptime during core hours | SOW 4.1
EVT-004 | 2025-10-24 | CLM-004 | CPT Chen (ACOR) | Staffing report received Monday 1430 — 2.5 hrs late | \\fileserver\TO-Evidence\EVT-004.pdf | Y | Weekly staffing report due every Monday by 1200 | SOW 5.3
EVT-005 | 2025-11-22 | CLM-005 | CPT Chen (ACOR) | Personnel audit: 2 of 14 have expired interim clearances | \\fileserver\TO-Evidence\EVT-005.pdf | Y | All personnel shall hold current security clearance at TS/SCI | CDRL A001
EVT-006 | 2025-10-28 | CLM-006 | Mr. Davis (KO) | Help desk avg response: 22 min — exceeds 15-min SLA | \\fileserver\TO-Evidence\EVT-006.pdf | N | Help desk response time shall not exceed 15 minutes | CDRL A003
EVT-007 | 2025-12-13 | CLM-007 | CPT Chen (ACOR) | Q1 review delivered on time; content reviewed | \\fileserver\TO-Evidence\EVT-007.pdf | Y | Quarterly program review briefing by 10th of quarter | CDRL A005
EVT-008 | 2025-12-02 | CLM-008 | CPT Chen (ACOR) | Code coverage 71% on Sprint 14 deliverable | \\fileserver\TO-Evidence\EVT-008.pdf | Y | All code commits shall include unit test coverage above 80% | PWS 3.2.1
EVT-009 | 2025-11-19 | CLM-009 | SSG Miller (QA) | On-call tech unreachable 45 min during Sev 1 | \\fileserver\TO-Evidence\EVT-009.pdf | Y | Contractor shall provide 24/7 on-call support for critical systems | PWS 4.1.3
EVT-010 | 2025-11-06 | CLM-010 | CPT Chen (ACOR) | Backup log: 3 failed backups week of 3/15 | \\fileserver\TO-Evidence\EVT-010.pdf | N | Data backup completed nightly with verification log weekly | QASP 2
EVT-011 | 2025-11-05 | CLM-011 | Ms. Patel (PM) | Dashboard 15-min gap during maintenance | \\fileserver\TO-Evidence\EVT-011.pdf | N | Network monitoring dashboard updated real-time 5-min refresh | QASP 4
EVT-012 | 2025-11-19 | CLM-012 | CPT Chen (ACOR) | Incident response: 47 min for P1 outage 3/22 | \\fileserver\TO-Evidence\EVT-012.pdf | N | Incident response initiated within 30 minutes of detection | TO Mod 001
EVT-013 | 2025-11-26 | CLM-013 | CPT Chen (ACOR) | Documentation does not conform to DI-MGMT-81466 | \\fileserver\TO-Evidence\EVT-013.pdf | Y | All documentation per DI-MGMT-81466 | TO Mod 003
EVT-014 | 2025-10-20 | CLM-014 | Ms. Patel (PM) | Training materials reference deprecated v2.1 | \\fileserver\TO-Evidence\EVT-014.pdf | Y | Training materials updated within 30 days of system change | Policy 24-01
EVT-015 | 2025-11-19 | CLM-015 | CPT Chen (ACOR) | Transition plan submitted day 85 — 5 days late | \\fileserver\TO-Evidence\EVT-015.pdf | Y | Transition plan delivered 90 days before PoP end | COR Dir 25-001
EVT-016 | 2025-12-27 | CLM-016 | CPT Chen (ACOR) | NIST 800-171 self-assessment: 87/110 — 3 POAMs open | \\fileserver\TO-Evidence\EVT-016.pdf | Y | Comply with NIST 800-171 requirements | SOW 3.1
EVT-017 | 2025-12-18 | CLM-017 | Ms. Patel (PM) | CM plan last updated 6 months ago — outdated | \\fileserver\TO-Evidence\EVT-017.pdf | N | Configuration management plan maintained and current | SOW 3.2
EVT-018 | 2025-11-03 | CLM-018 | CPT Chen (ACOR) | Critical CVE patches applied 96 hrs — 24 hrs over | \\fileserver\TO-Evidence\EVT-018.pdf | Y | System patches applied within 72 hours for critical CVEs | SOW 4.1
EVT-019 | 2025-11-16 | CLM-019 | SSG Miller (QA) | Travel without prior COR written approval | \\fileserver\TO-Evidence\EVT-019.pdf | N | All travel requires prior written COR approval | SOW 5.3
EVT-020 | 2025-11-18 | CLM-020 | Ms. Patel (PM) | Financial report delivered 15th — 5 days late | \\fileserver\TO-Evidence\EVT-020.pdf | N | Monthly financial report with cost/burn-rate by 10th | CDRL A001
EVT-021 | 2025-12-29 | CLM-021 | Mr. Davis (KO) | Risk register not updated 2 consecutive reviews | \\fileserver\TO-Evidence\EVT-021.pdf | N | Risk register maintained and reviewed at each program review | CDRL A003
EVT-022 | 2025-11-13 | CLM-022 | SSG Miller (QA) | Key personnel departure: 5 days notice (req: 30) | \\fileserver\TO-Evidence\EVT-022.pdf | Y | Key personnel changes require 30-day advance notice | CDRL A005
EVT-023 | 2025-12-18 | CLM-023 | MAJ Torres (COR) | GFE laptop #47 missing from log 3 months | \\fileserver\TO-Evidence\EVT-023.pdf | Y | All GFE tracked in property log | PWS 3.2.1
EVT-024 | 2025-10-30 | CLM-024 | CPT Chen (ACOR) | Test plan submitted but not approved before testing | \\fileserver\TO-Evidence\EVT-024.pdf | Y | Test plan approved before system testing begins | PWS 4.1.3
EVT-025 | 2025-12-09 | CLM-025 | MAJ Torres (COR) | Deliverable acceptance took 18 business days (req: 10) | \\fileserver\TO-Evidence\EVT-025.pdf | N | Final delivery acceptance within 10 business days | QASP 2

## Reviews
ReviewID | Date | ClaimID | EventID | Finding | Drift | Severity | Reviewer | Days Since Event | ⬅ Claim (auto)
REV-001 | 2025-12-19 | CLM-001 | EVT-001 | Drift confirmed: 3 of 4 reports late. Pattern. | N | Critical | Mr. Jackson (QA) | -4 | Contractor shall deliver monthly status report by 5th business day
REV-002 | 2026-01-06 | CLM-002 | EVT-002 | Security findings Critical. Cannot accept deliverable. | Y | Low | MAJ Torres (COR) | 72 | All software deliverables shall pass security scan before acceptance
REV-003 | 2026-01-26 | CLM-003 | EVT-003 | Uptime below threshold 2 consecutive months. Systemic. | Y | High | Ms. Kim (Audit) | 56 | Contractor shall maintain 98% system uptime during core hours
REV-004 | 2026-01-21 | CLM-004 | EVT-004 | Minor deviation. Verbal counseling. Monitor 4 weeks. | Y | Low | CPT Chen (ACOR) | 89 | Weekly staffing report due every Monday by 1200
REV-005 | 2025-12-07 | CLM-005 | EVT-005 | Clearance gap: immediate risk. Cannot access SCIF. | N | Medium | Mr. Davis (KO) | 15 | All personnel shall hold current security clearance at TS/SCI
REV-006 | 2025-12-28 | CLM-006 | EVT-006 | SLA breach: 5 of 8 weeks exceeded. Not isolated. | Y | High | Mr. Jackson (QA) | 61 | Help desk response time shall not exceed 15 minutes
REV-007 | 2026-01-03 | CLM-007 | EVT-007 | Content adequate. Delivery format needs improvement. | Y | Low | MAJ Torres (COR) | 21 | Quarterly program review briefing by 10th of quarter
REV-008 | 2026-01-19 | CLM-008 | EVT-008 | Coverage deficit is quality risk. Cannot accept. | Y | Medium | Ms. Kim (Audit) | 48 | All code commits shall include unit test coverage above 80%
REV-009 | 2025-11-19 | CLM-009 | EVT-009 | On-call failure during Sev 1: critical performance issue. | Y | Medium | CPT Chen (ACOR) | 0 | Contractor shall provide 24/7 on-call support for critical systems
REV-010 | 2026-01-08 | CLM-010 | EVT-010 | Backup failures: data loss risk. Corrective action required. | N | Low | Mr. Davis (KO) | 63 | Data backup completed nightly with verification log weekly
REV-011 | 2026-01-15 | CLM-011 | EVT-011 | Dashboard gap acceptable during maintenance. | Y | Critical | Mr. Jackson (QA) | 71 | Network monitoring dashboard updated real-time 5-min refresh
REV-012 | 2025-11-02 | CLM-012 | EVT-012 | Response time failure: critical. Playbook not followed. | Y | High | MAJ Torres (COR) | -17 | Incident response initiated within 30 minutes of detection
REV-013 | 2025-12-09 | CLM-013 | EVT-013 | Format non-conformance correctable. Issue COR direction. | Y | Low | Ms. Kim (Audit) | 13 | All documentation per DI-MGMT-81466
REV-014 | 2025-11-30 | CLM-014 | EVT-014 | Outdated training: operational risk. Immediate update. | N | Low | CPT Chen (ACOR) | 41 | Training materials updated within 30 days of system change
REV-015 | 2025-11-10 | CLM-015 | EVT-015 | Late delivery within tolerance. Issue verbal notice. | N | Low | Mr. Davis (KO) | -9 | Transition plan delivered 90 days before PoP end
REV-016 | 2026-01-07 | CLM-016 | EVT-016 | NIST compliance gap requires formal remediation plan. | Y | Medium | Mr. Jackson (QA) | 11 | Comply with NIST 800-171 requirements
REV-017 | 2026-01-23 | CLM-017 | EVT-017 | Outdated CM plan creates configuration drift risk. | N | Medium | MAJ Torres (COR) | 36 | Configuration management plan maintained and current
REV-018 | 2025-12-03 | CLM-018 | EVT-018 | Patch delay borderline. Monitor; escalate if repeated. | N | Critical | Ms. Kim (Audit) | 30 | System patches applied within 72 hours for critical CVEs
REV-019 | 2025-11-27 | CLM-019 | EVT-019 | Unauthorized travel: contract compliance violation. | N | Medium | CPT Chen (ACOR) | 11 | All travel requires prior written COR approval
REV-020 | 2025-12-09 | CLM-020 | EVT-020 | Late financial report impacts visibility. Escalate. | N | High | Mr. Davis (KO) | 21 | Monthly financial report with cost/burn-rate by 10th

## Patches
PatchID | Date | ReviewID | ClaimID | Correction | Rationale | Approver | Status | Days to Patch | ⬅ Finding (auto)
PAT-001 | 2025-12-31 | REV-001 | CLM-001 | COR letter: contractor submit CAP by April 15 | Review REV-001 identified drift. | Ms. Patel (PM) | Applied | 12 | Drift confirmed: 3 of 4 reports late. Pattern.
PAT-002 | 2026-01-01 | REV-002 | CLM-002 | Deliverable returned. Remediate 3 Critical, resubmit. | Review REV-002 identified drift. | Mr. Davis (KO) | Pending | -5 | Security findings Critical. Cannot accept deliverable.
PAT-003 | 2025-12-06 | REV-003 | CLM-003 | PIP required within 14 days. Monitor 2 months. | Review REV-003 identified drift. | COL Richardson (DPM) | Approved | -51 | Uptime below threshold 2 consecutive months. Systemic.
PAT-004 | 2025-11-13 | REV-004 | CLM-004 | Verbal counseling documented. No formal action. | Review REV-004 identified drift. | Ms. Patel (PM) | Approved | -69 | Minor deviation. Verbal counseling. Monitor 4 weeks.
PAT-005 | 2025-11-07 | REV-005 | CLM-005 | Resolve clearance gaps 10 days or replace personnel. | Review REV-005 identified drift. | Ms. Patel (PM) | Applied | -30 | Clearance gap: immediate risk. Cannot access SCIF.
PAT-006 | 2026-01-14 | REV-006 | CLM-006 | Cure notice drafted. 10-day cure period. | Review REV-006 identified drift. | Mr. Davis (KO) | Approved | 17 | SLA breach: 5 of 8 weeks exceeded. Not isolated.
PAT-007 | 2026-01-19 | REV-007 | CLM-007 | COR direction: reformat per DI-MGMT-81466. | Review REV-007 identified drift. | COL Richardson (DPM) | Approved | 16 | Content adequate. Delivery format needs improvement.
PAT-008 | 2025-11-05 | REV-008 | CLM-008 | Sprint 15 must show >80% coverage or reject. | Review REV-008 identified drift. | Ms. Patel (PM) | Pending | -75 | Coverage deficit is quality risk. Cannot accept.
PAT-009 | 2026-02-03 | REV-009 | CLM-009 | Revise on-call procedures. Updated roster 7 days. | Review REV-009 identified drift. | Ms. Patel (PM) | Applied | 76 | On-call failure during Sev 1: critical performance issue.
PAT-010 | 2025-11-12 | REV-010 | CLM-010 | Implement auto backup verification. Daily report 30 days. | Review REV-010 identified drift. | Mr. Davis (KO) | Approved | -57 | Backup failures: data loss risk. Corrective action required.
PAT-011 | 2025-11-13 | REV-011 | CLM-011 | No action required. Gap within maintenance window. | Review REV-011 identified drift. | COL Richardson (DPM) | Pending | -63 | Dashboard gap acceptable during maintenance.
PAT-012 | 2025-12-17 | REV-012 | CLM-012 | Conduct incident response drill within 14 days. | Review REV-012 identified drift. | Ms. Patel (PM) | Pending | 45 | Response time failure: critical. Playbook not followed.
PAT-013 | 2026-01-09 | REV-013 | CLM-013 | Update all documentation to current template 30 days. | Review REV-013 identified drift. | Ms. Patel (PM) | Approved | 31 | Format non-conformance correctable. Issue COR direction.
PAT-014 | 2025-12-10 | REV-014 | CLM-014 | Update training materials to v3.0 within 21 days. | Review REV-014 identified drift. | Mr. Davis (KO) | Applied | 10 | Outdated training: operational risk. Immediate update.
PAT-015 | 2026-01-06 | REV-015 | CLM-015 | Written notice. Next late triggers cure notice. | Review REV-015 identified drift. | COL Richardson (DPM) | Approved | 57 | Late delivery within tolerance. Issue verbal notice.

## Apply
ApplyID | Date | PatchID | ClaimID | Action Taken | Evidence | Verified By | Days to Apply | ⬅ Correction (auto)
APL-001 | 2026-01-23 | PAT-001 | CLM-001 | CAP received Apr 14. Accepted. April report on time. Updated. | \\fileserver\TO-Evidence\APL-001_closeout.pdf | MAJ Torres (COR) | 23 | COR letter: contractor submit CAP by April 15
APL-002 | 2026-02-15 | PAT-002 | CLM-002 | Resubmission: 3 Critical remediated. Deliverable accepted. | \\fileserver\TO-Evidence\APL-002_closeout.pdf | Mr. Davis (KO) | 45 | Deliverable returned. Remediate 3 Critical, resubmit.
APL-003 | 2026-01-27 | PAT-003 | CLM-003 | PIP submitted. March uptime 99.1%. Monitoring continues. | \\fileserver\TO-Evidence\APL-003_closeout.pdf | CPT Chen (ACOR) | 52 | PIP required within 14 days. Monitor 2 months.
APL-004 | 2025-12-16 | PAT-004 | CLM-004 | Verbal counseling noted. Next 4 reports on time. Closed. | \\fileserver\TO-Evidence\APL-004_closeout.pdf | CPT Chen (ACOR) | 33 | Verbal counseling documented. No formal action.
APL-005 | 2026-02-26 | PAT-005 | CLM-005 | 2 personnel replaced 8 days. Clearance verified. Restored. | \\fileserver\TO-Evidence\APL-005_closeout.pdf | CPT Chen (ACOR) | 111 | Resolve clearance gaps 10 days or replace personnel.
APL-006 | 2025-12-09 | PAT-006 | CLM-006 | Cure notice issued. SLA met 4 weeks. Closed. | \\fileserver\TO-Evidence\APL-006_closeout.pdf | Mr. Jackson (QA) | -36 | Cure notice drafted. 10-day cure period.
APL-007 | 2025-11-27 | PAT-007 | CLM-007 | Q2 deliverable reformatted. Accepted. Compliance confirmed. | \\fileserver\TO-Evidence\APL-007_closeout.pdf | CPT Chen (ACOR) | -53 | COR direction: reformat per DI-MGMT-81466.
APL-008 | 2025-12-30 | PAT-008 | CLM-008 | Sprint 15 coverage: 84%. Met. Accepted. | \\fileserver\TO-Evidence\APL-008_closeout.pdf | CPT Chen (ACOR) | 55 | Sprint 15 must show >80% coverage or reject.
APL-009 | 2026-01-06 | PAT-009 | CLM-009 | Revised roster received. Drill successful. Verified. | \\fileserver\TO-Evidence\APL-009_closeout.pdf | CPT Chen (ACOR) | -28 | Revise on-call procedures. Updated roster 7 days.
APL-010 | 2026-02-16 | PAT-010 | CLM-010 | Auto verification running. 30-day 100% success. Closed. | \\fileserver\TO-Evidence\APL-010_closeout.pdf | Mr. Jackson (QA) | 96 | Implement auto backup verification. Daily report 30 days.